## Draft Timeline v0
OneTake — Draft Timeline (v0)
DRAFT — For PM Review & Collaboration • Not a final plan — designed to be discussed, reshuffled, and owned together
Prepared: April 15, 2026 • Author: Steven Junop • For: Abi (Senior PM) • Start: April 21, 2026
Track | Workstream | Week 1 Apr 21–25 | Week 2 Apr 28–May 2 | Week 3 May 5–9 | Week 4 May 12–16 | Week 5 May 19–23 | Week 6 May 26–30 | Owner | Dependencies / Notes
OneTake Pipeline (Engineering) | Internal Validation | Run 2–3 test campaigns end-to-end, fix issues | [5 empty] | Steven | Campaigns selected with Jenn
| WP Auto-Publish |  | Wire WP MCP into Stage 1 Per-location pages + URL capture |  |  |  |  | Steven | WP credentials secured
| Auto UTM Linking |  | WP publish → auto-create tracked links → notify recruiter |  |  |  |  | Steven | Depends on WP auto-publish
| Organic Content |  |  | Social post copy (LI, FB, X) Flyer + poster + social card formats |  |  |  | Steven | Different tone from paid — needs review
| Video Pipeline |  |  | Kling Stage 5 on real campaigns |  |  |  | Steven | Kling credits needed
| Polish & Stabilize |  |  |  | Bug fixes from pilot feedback 3–5 campaigns fully validated |  |  | Steven
Tracking & Attribution (GTM / GA4) | GTM Bug Fixes | Fix 5 existing bugs (utm typo, property ID, conversions, survey params) | [5 empty] | Steven + Poola | GTM publish access required
| New Event Tags | 7 new tags + UTM persist + visitor ID + cross-domain | [5 empty] | Steven + Poola | Coordinate with Poola
| GA4 Dimensions |  | 12 custom dimensions + initial QA |  |  |  |  | Steven | GA4 admin access required
| Reporting Dashboard |  |  | Looker Studio dashboard Verify data flow |  |  |  | Steven | Needs 1–2 weeks of clean data
Team Enablement (Recruiters / Designers) | Designer Testing | Miguel:portal use on test campaigns | Ongoing — feedback on gallery + edit tools |  |  |  |  | Miguel
| Internal Pilot |  | Steven + Jenn run 2–3 campaigns, document pain points |  |  |  |  | Steven + Jenn
| Recruiter Pilot |  |  | 1–2 recruiter volunteers supervised intake walkthrough |  |  |  | Jenn (recruit) Steven (support) | Jenn to identify volunteers
| Training & Docs |  |  | Record Loom walkthroughs for each portal | Full recruiter team training session |  |  | Steven
| Agency Handoff |  |  |  | First real magic link handoff — gather feedback |  |  | Steven + Jenn | Need agency contact info
Integrations (Microsoft Ecosystem) | IT Request Submission | Send integration reqs to IT (SSO, Teams, Outlook, SharePoint) | [5 empty] | Steven | P1 — unblocks everything
| Teams Webhook (Prod) |  | Get production webhook URL from IT |  |  |  |  | IT Admin | Currently using test URL
| Outlook / Graph API |  | App registration for @centific.com sending |  |  |  |  | IT Admin | Currently using test setup
| Azure AD SSO |  |  | Clerk SAML/Entra ID ↔ Azure AD Enterprise app config |  |  |  | IT Admin + Steven | Blocks internal rollout
| SharePoint (P2) |  |  |  | Auto-create campaign folders, save assets |  |  | IT Admin + Steven | Nice to have — not blocking
Analytics & Reporting (VYRA Visualize) | Data Accumulation |  |  | Live campaigns generating UTM click data | Continue accumulating production data |  |  | — | Blocked until Track 2 live
| API Port |  |  |  | Port SRC Command Center API to Nova data model | KPI Dashboard + channel rollups in UI |  | Steven | Depends on GA4 API access
| RevBrain + Funnel |  |  |  |  | RevBrain AI recs + funnel drilldown |  | Steven | Needs ad platform API creds
| Exports & Sharing | [5 empty] | PDF/CSV reports Public share tokens | Steven | For Adam pitch deck
KEY MILESTONES |  | GTM bugs fixed (Day 5) | WP auto-publish live Designer testing | Recruiter pilot starts SSO configured | Full team trained Agency test handoff | KPI Dashboard live RevBrain active | Adam pitch ready Exports + share links
OPEN DEPENDENCIES — Items that need PM/Org action
Priority | Dependency |  |  | Owner |  | Impact
P1 | Azure AD SSO configuration |  |  | IT Admin |  | Blocks internal team access — using Clerk dev keys
P1 | Teams production webhook URL |  |  | IT Admin |  | Currently using test webhook
P1 | Outlook Graph API app registration |  |  | IT Admin |  | Needed for @centific.com notifications
P1 | GTM publish access (GTM-NR965959) |  |  | Poola / IT |  | Blocks all tracking fixes
P1 | GA4 admin access (property 330157295) |  |  | Poola / IT |  | Blocks custom dimensions + conversion marking
P1 | 1–2 recruiter pilot volunteers |  |  | Jenn |  | Needed by Week 3
P1 | Agency contact for magic link test |  |  | Jenn |  | Needed by Week 4
P2 | SharePoint site URL + Graph API permissions |  |  | IT Admin |  | Nice to have — not blocking launch
P2 | Ad platform API creds (Meta, LinkedIn, Google) |  |  | Steven + IT |  | Blocks Track 5 analytics
SUCCESS METRICS — How we'll know this is working
Metric |  | Before Nova |  | With Nova |  | How to Measure
Time: JD → campaign package |  | 3–5 business days |  | 30 min + review |  | Timestamp: intake submit → final approval
Creatives per campaign |  | 2–4 generic designs |  | 15–30+ per-persona |  | Asset count in system
Cost per campaign |  | Agency hours + designer time |  | ~$0 (free AI + Vercel) |  | Infrastructure cost tracking
Recruiter time spent |  | 4–8 hours coordinating |  | 15 min intake + 10 min links |  | Session tracking
Tracking accuracy |  | Broken (7,600 paid visitors → 0 conversions) |  | Full cross-device attribution |  | GA4 conversion reports
This is a working draft. Timelines are estimates — designed to be adjusted together. All tracks can shift based on IT response times and pilot feedback.