## Gantt Chart
Nova — Gantt Chart & Integration Map
8 Tracks • 134 Tasks • 25 Integrations • Business Days Only (No Weekends)
Prepared: April 17, 2026 • Start: April 21, 2026 (Monday) • Target End: May 28, 2026
WBS | Task Name | Owner | Status | Integration / Dependency | Days | Start | End | Week 1 Apr 21–25 | Week 2 Apr 28–May 2 | Week 3 May 5–9 | Week 4 May 12–16 | Week 5 May 19–23 | Week 6 May 26–30
1 | Pipeline & Quality |  |  |  | 20 | 2026-04-21 | 2026-05-18 | ■ | ■ | ■ | ■
1.1 | Stage 4 — HTML Template Tuning | Steven | In Progress |  | 5 | 2026-04-21 | 2026-04-25 | ■
1.1.1 | Audit existing templates + grading results | Steven | In Progress |  | 1 | 2026-04-21 | 2026-04-21 | ■
1.1.2 | New feed format templates (3 variants) | Steven | Planned | GLM-5 via OpenRouter | 1 | 2026-04-22 | 2026-04-22 | ■
1.1.3 | New story/carousel templates (3 variants) | Steven | Planned | GLM-5 via OpenRouter | 1 | 2026-04-23 | 2026-04-23 | ■
1.1.4 | Typography + spacing hierarchy system | Steven | Planned |  | 1 | 2026-04-24 | 2026-04-24 | ■
1.1.5 | Test all against 8-cat grading matrix | Steven | Planned | Playwright (Chromium) | 1 | 2026-04-25 | 2026-04-25 | ■
1.2 | Stage 6 — Landing Page Template Design | Steven | In Progress |  | 5 | 2026-04-21 | 2026-04-25 | ■
1.2.1 | Hero section variants (3 concepts) | Steven | In Progress |  | 1 | 2026-04-21 | 2026-04-21 | ■
1.2.2 | Body sections (testimonials, FAQ, benefits) | Steven | Planned |  | 1 | 2026-04-22 | 2026-04-22 | ■
1.2.3 | Mobile-responsive + CTA placement | Steven | Planned |  | 1 | 2026-04-23 | 2026-04-23 | ■
1.2.4 | Per-persona visual adaptation logic | Steven | Planned | Vercel Blob | 1 | 2026-04-24 | 2026-04-24 | ■
1.2.5 | Template selection logic in Stage 6 | Steven | Planned | Jinja2 | 1 | 2026-04-25 | 2026-04-25 | ■
1.3 | Stage 3 — Email + Job Posting Copy | Steven | Planned |  | 3 | 2026-04-28 | 2026-04-30 |  | ■
1.3.1 | Add email sequence output to Stage 3 | Steven | Planned | Kimi K2.5 via OpenRouter | 1 | 2026-04-28 | 2026-04-28 |  | ■
1.3.2 | Add job posting copy output | Steven | Planned | Kimi K2.5 via OpenRouter | 1 | 2026-04-29 | 2026-04-29 |  | ■
1.3.3 | Surface email/JD copy in marketing view | Steven | Planned |  | 1 | 2026-04-30 | 2026-04-30 |  | ■
1.4 | Stage 2 — Persona Fix + Regeneration | Steven | Planned |  | 2 | 2026-04-28 | 2026-04-29 |  | ■
1.4.1 | Regen Stage 2 for existing campaigns | Steven | Planned | Seedream 4.5 via NIM | 1 | 2026-04-28 | 2026-04-28 |  | ■
1.4.2 | Verify 3 actors/persona + grouping | Steven | Planned |  | 1 | 2026-04-29 | 2026-04-29 |  | ■
1.5 | Organic Content (Posts, Flyers, Posters) | Steven | Planned |  | 4 | 2026-05-01 | 2026-05-06 |  | ■ | ■
1.5.1 | Organic copy prompts (LI, FB, X) | Steven | Planned | Kimi K2.5 via OpenRouter | 1 | 2026-05-01 | 2026-05-01 |  | ■
1.5.2 | Print format dimensions (A4, A3, card) | Steven | Planned |  | 1 | 2026-05-04 | 2026-05-04
1.5.3 | Composition templates for print | Steven | Planned | GLM-5 + Playwright | 1 | 2026-05-05 | 2026-05-05 |  |  | ■
1.5.4 | Gallery integration + designer flow | Steven | Planned |  | 1 | 2026-05-06 | 2026-05-06 |  |  | ■
1.6 | Stage 5 — Video Pipeline | Steven | Planned |  | 3 | 2026-05-07 | 2026-05-11 |  |  | ■
1.6.1 | Kling credits + test on real campaign | Steven | Planned | Kling 3.0 API | 1 | 2026-05-07 | 2026-05-07 |  |  | ■
1.6.2 | UGC script gen + storyboard | Steven | Planned | Kimi K2.5 via OpenRouter | 1 | 2026-05-08 | 2026-05-08 |  |  | ■
1.6.3 | TTS + lip sync + FFmpeg | Steven | Planned | Coqui TTS + Wav2Lip | 1 | 2026-05-11 | 2026-05-11
1.7 | End-to-End Campaign Testing | Steven + Jenn | Planned |  | 5 | 2026-05-12 | 2026-05-18 |  |  |  | ■
1.7.1 | Campaign 1 — full pipeline | Steven + Jenn | Planned | All integrations | 1 | 2026-05-12 | 2026-05-12 |  |  |  | ■
1.7.2 | Campaign 2 — different region/lang | Steven + Jenn | Planned |  | 1 | 2026-05-13 | 2026-05-13 |  |  |  | ■
1.7.3 | Campaign 3 — onsite task type | Steven + Jenn | Planned |  | 1 | 2026-05-14 | 2026-05-14 |  |  |  | ■
1.7.4 | Bug fixes from testing | Steven | Planned |  | 1 | 2026-05-15 | 2026-05-15 |  |  |  | ■
1.7.5 | Quality sign-off | Steven + Jenn | Planned |  | 1 | 2026-05-18 | 2026-05-18
2 | Microsoft Integrations |  |  |  | 15 | 2026-04-21 | 2026-05-04 | ■ | ■
2.1 | Azure AD SSO (SAML) | IT + Steven | Not Started | Azure AD + Clerk SAML | 5 | 2026-04-21 | 2026-04-25 | ■
2.1.1 | IT: Create Azure AD enterprise app | IT Admin | Not Started | Azure Active Directory | 2 | 2026-04-21 | 2026-04-22 | ■
2.1.2 | IT: Provide SAML metadata URL | IT Admin | Not Started | Azure AD SAML | 1 | 2026-04-23 | 2026-04-23 | ■
2.1.3 | Configure Clerk SAML connection | Steven | Not Started | Clerk SSO | 1 | 2026-04-24 | 2026-04-24 | ■
2.1.4 | Test SSO login + role provisioning | Steven | Not Started | Clerk + Azure AD | 1 | 2026-04-25 | 2026-04-25 | ■
2.2 | Microsoft Teams Notifications | IT + Steven | Partial | Teams Webhooks | 3 | 2026-04-21 | 2026-04-23 | ■
2.2.1 | IT: Create prod webhook URL | IT Admin | Not Started | Teams Admin Center | 1 | 2026-04-21 | 2026-04-21 | ■
2.2.2 | Swap test → prod webhook URL | Steven | Not Started | Vercel env vars | 1 | 2026-04-22 | 2026-04-22 | ■
2.2.3 | Test adaptive card delivery E2E | Steven | Not Started | Teams Webhooks | 1 | 2026-04-23 | 2026-04-23 | ■
2.3 | Outlook Email Notifications | IT + Steven | Not Started | Microsoft Graph API | 3 | 2026-04-24 | 2026-04-28 | ■ | ■
2.3.1 | IT: Register Graph API app (Mail.Send) | IT Admin | Not Started | Azure App Registration | 1 | 2026-04-24 | 2026-04-24 | ■
2.3.2 | Configure Graph API creds in Nova | Steven | Not Started | Microsoft Graph SDK | 1 | 2026-04-25 | 2026-04-25 | ■
2.3.3 | Test email from @centific.com | Steven | Not Started | Graph API + Outlook | 1 | 2026-04-28 | 2026-04-28 |  | ■
2.4 | SharePoint Campaign Folders | IT + Steven | Not Started | Microsoft Graph API | 4 | 2026-04-29 | 2026-05-02 |  | ■
2.4.1 | IT: Grant Sites.ReadWrite.All | IT Admin | Not Started | Azure App Permissions | 1 | 2026-04-29 | 2026-04-29 |  | ■
2.4.2 | IT: Confirm site + folder structure | IT + Jenn | Not Started | SharePoint Online | 1 | 2026-04-30 | 2026-04-30 |  | ■
2.4.3 | Build auto-folder on approval | Steven | Not Started | Graph API (DriveItems) | 1 | 2026-05-01 | 2026-05-01 |  | ■
2.4.4 | Auto-upload approved assets | Steven | Not Started | Graph API + Blob | 1 | 2026-05-02 | 2026-05-02 |  | ■
3 | AI & Model Providers |  |  |  | 10 | 2026-04-21 | 2026-05-11 | ■ | ■ | ■
3.1 | OpenRouter (LLM Gateway) | Steven | Active | OpenRouter API | 2 | 2026-04-21 | 2026-04-22 | ■
3.1.1 | Verify Kimi K2.5 quota (Stages 1, 3) | Steven | Active | OpenRouter | 1 | 2026-04-21 | 2026-04-21 | ■
3.1.2 | Verify GLM-5 quota (Stage 4) | Steven | Active | OpenRouter | 1 | 2026-04-22 | 2026-04-22 | ■
3.2 | NVIDIA NIM (Image Gen) | Steven | Active | NVIDIA NIM API | 2 | 2026-04-21 | 2026-04-22 | ■
3.2.1 | Verify Seedream 4.5 credits | Steven | Active | NIM — Stage 2 | 1 | 2026-04-21 | 2026-04-21 | ■
3.2.2 | Test 15-key rotation | Steven | Active | NIM key rotation | 1 | 2026-04-22 | 2026-04-22 | ■
3.3 | Kling 3.0 (Video Gen) | Steven | Planned | Kling API | 2 | 2026-05-07 | 2026-05-08 |  |  | ■
3.3.1 | Load credits + verify API | Steven | Planned | Kling — Stage 5 | 1 | 2026-05-07 | 2026-05-07 |  |  | ■
3.3.2 | Test multi-shot video gen | Steven | Planned | Kling + FFmpeg | 1 | 2026-05-08 | 2026-05-08 |  |  | ■
3.4 | MLX Local Inference | Steven | Active | MLX + Metal GPU | 1 | 2026-04-23 | 2026-04-23 | ■
3.5 | Gemma 4 (VQA) | Steven | Active | Gemma via NIM/OR | 1 | 2026-04-24 | 2026-04-24 | ■
3.6 | Coqui TTS + Wav2Lip | Steven | Planned | Local torch + opencv | 1 | 2026-05-11 | 2026-05-11
4 | External Platforms |  |  |  | 8 | 2026-04-21 | 2026-04-28 | ■ | ■
4.1 | WordPress (Job CPT + ACF) | Steven | Done | WP REST API + ACF |  | 2026-04-21 | 2026-04-21 | ■
4.1.1 | Job CPT auto-publish | Steven | Done | WP REST API v2 |  | 2026-04-21 | 2026-04-21 | ■
4.1.2 | ACF apply_job repeater | Steven | Done | ACF REST API |  | 2026-04-21 | 2026-04-21 | ■
4.1.3 | Yoast SEO meta via excerpt | Steven | Done | Yoast + WP REST |  | 2026-04-21 | 2026-04-21 | ■
4.1.4 | Taxonomy tagging | Steven | Done | WP Taxonomies |  | 2026-04-21 | 2026-04-21 | ■
4.2 | Vercel (Hosting + Blob) | Steven | Active | Vercel Platform | 2 | 2026-04-21 | 2026-04-22 | ■
4.2.1 | Production deploy + CI | Steven | Done | Vercel CLI + GH Actions |  | 2026-04-21 | 2026-04-21 | ■
4.2.2 | go.oneforma.com domain | IT + Steven | Pending IT | DNS CNAME + Vercel | 2 | 2026-04-21 | 2026-04-22 | ■
4.3 | Neon Postgres | Steven | Active | Neon Serverless | 1 | 2026-04-21 | 2026-04-21 | ■
4.3.1 | DB operational | Steven | Done | @neondatabase + asyncpg |  | 2026-04-21 | 2026-04-21 | ■
4.3.2 | Rotate DB password | Steven | Pending | Neon Console | 1 | 2026-04-21 | 2026-04-21 | ■
4.4 | Clerk (Auth) | Steven | Active | Clerk SDK | 1 | 2026-04-25 | 2026-04-25 | ■
4.4.1 | Swap to prod keys (after SSO) | Steven | Blocked | Clerk + Azure AD | 1 | 2026-04-25 | 2026-04-25 | ■
4.5 | Figma (Design Handoff) | Steven + Miguel | Active | Figma API | 1 | 2026-04-28 | 2026-04-28 |  | ■
4.5.1 | Test push-to-Figma on live campaign | Miguel | Planned | Figma PAT | 1 | 2026-04-28 | 2026-04-28 |  | ■
4.6 | Playwright (Rendering) | Steven | Done | Chromium headless |  | 2026-04-21 | 2026-04-21 | ■
5 | Analytics & Ad Platforms |  |  |  | 10 | 2026-05-18 | 2026-05-28 |  |  |  |  | ■ | ■
5.1 | Google Analytics 4 | Steven | Planned | GA4 Data API | 3 | 2026-05-18 | 2026-05-20 |  |  |  |  | ■
5.1.1 | Get GA4 property access | Steven + Jenn | Planned | Google Cloud Console | 1 | 2026-05-18 | 2026-05-18
5.1.2 | Connect GA4 API to Visualize | Steven | Planned | GA4 API + OAuth | 1 | 2026-05-19 | 2026-05-19 |  |  |  |  | ■
5.1.3 | UTM attribution mapping | Steven | Planned | GA4 + tracked_links | 1 | 2026-05-20 | 2026-05-20 |  |  |  |  | ■
5.2 | Meta Ads (FB/IG) | Steven | Planned | Meta Marketing API | 2 | 2026-05-21 | 2026-05-22 |  |  |  |  | ■
5.2.1 | Get Meta Business Manager access | Steven + Jenn | Planned | Meta Business Suite | 1 | 2026-05-21 | 2026-05-21 |  |  |  |  | ■
5.2.2 | Connect Meta API to Visualize | Steven | Planned | Meta Marketing API v19 | 1 | 2026-05-22 | 2026-05-22 |  |  |  |  | ■
5.3 | LinkedIn Campaign Manager | Steven | Planned | LinkedIn Marketing API | 2 | 2026-05-25 | 2026-05-26 | [5 empty] | ■
5.3.1 | Get LinkedIn ad account access | Steven + Jenn | Planned | LinkedIn Campaign Mgr | 1 | 2026-05-25 | 2026-05-25
5.3.2 | Connect LinkedIn API to Visualize | Steven | Planned | LinkedIn Marketing API | 1 | 2026-05-26 | 2026-05-26 | [5 empty] | ■
5.4 | Google Ads | Steven | Planned | Google Ads API | 2 | 2026-05-27 | 2026-05-28 | [5 empty] | ■
5.4.1 | Get Google Ads account access | Steven + Jenn | Planned | Google Ads Console | 1 | 2026-05-27 | 2026-05-27 | [5 empty] | ■
5.4.2 | Connect Google Ads API to Visualize | Steven | Planned | Google Ads API v16 | 1 | 2026-05-28 | 2026-05-28 | [5 empty] | ■
6 | Team Enablement |  |  |  | 15 | 2026-04-28 | 2026-05-14 |  | ■ | ■ | ■
6.1 | Designer Onboarding (Miguel) | Miguel | Planned | Figma + Designer Portal | 5 | 2026-04-28 | 2026-05-02 |  | ■
6.1.1 | Portal walkthrough + feedback | Steven + Miguel | Planned |  | 1 | 2026-04-28 | 2026-04-28 |  | ■
6.1.2 | Daily use on live campaigns (1 wk) | Miguel | Planned |  | 4 | 2026-04-29 | 2026-05-02 |  | ■
6.2 | Recruiter Pilot (1-2 volunteers) | Jenn | Planned |  | 5 | 2026-05-05 | 2026-05-09 |  |  | ■
6.2.1 | Identify pilot recruiters | Jenn | Planned |  | 1 | 2026-05-05 | 2026-05-05 |  |  | ■
6.2.2 | Supervised intake walkthrough | Steven | Planned |  | 1 | 2026-05-06 | 2026-05-06 |  |  | ■
6.2.3 | Pilots run real campaigns | Recruiters | Planned |  | 3 | 2026-05-07 | 2026-05-09 |  |  | ■
6.3 | Full Team Training + Agency | Steven | Planned |  | 3 | 2026-05-12 | 2026-05-14 |  |  |  | ■
6.3.1 | Record Loom walkthroughs (4 portals) | Steven | Planned |  | 1 | 2026-05-12 | 2026-05-12 |  |  |  | ■
6.3.2 | Live training — full recruiter team | Steven | Planned |  | 1 | 2026-05-13 | 2026-05-13 |  |  |  | ■
6.3.3 | Agency test handoff via magic link | Steven + Jenn | Planned |  | 1 | 2026-05-14 | 2026-05-14 |  |  |  | ■
7 | China Engineering Deployment |  |  |  | 8 | 2026-04-21 | 2026-04-28 | ■ | ■
7.1 | Codebase Review + Architecture | Michael | In Progress | GitHub (OneTake) | 3 | 2026-04-21 | 2026-04-23 | ■
7.1.1 | Michael reviews codebase + README | Michael | In Progress |  | 2 | 2026-04-21 | 2026-04-22 | ■
7.1.2 | Architecture decision | Michael + Steven | Planned |  | 1 | 2026-04-23 | 2026-04-23 | ■
7.2 | Azure VM Deployment | Michael | Planned | Docker + Azure | 3 | 2026-04-24 | 2026-04-28 | ■ | ■
7.2.1 | Provision Azure VM + Docker | Michael | Planned | Azure VM + Docker | 1 | 2026-04-24 | 2026-04-24 | ■
7.2.2 | Deploy worker container | Michael | Planned | Docker Compose | 1 | 2026-04-25 | 2026-04-25 | ■
7.2.3 | E2E verification on Azure | Michael + Steven | Planned | All integrations | 1 | 2026-04-28 | 2026-04-28 |  | ■
8 | Leadership Pitch |  |  |  | 8 | 2026-05-18 | 2026-05-28 |  |  |  |  | ■ | ■
8.1 | Prepare Pitch Materials | Steven | Planned |  | 5 | 2026-05-18 | 2026-05-22 |  |  |  |  | ■
8.1.1 | Compile campaign results + metrics | Steven | Planned | Nova DB + GA4 | 2 | 2026-05-18 | 2026-05-19 |  |  |  |  | ■
8.1.2 | Build pitch deck | Steven | Planned |  | 2 | 2026-05-20 | 2026-05-21 |  |  |  |  | ■
8.1.3 | Rehearse live demo flow | Steven | Planned |  | 1 | 2026-05-22 | 2026-05-22 |  |  |  |  | ■
8.2 | Leadership Presentations | Steven + Jenn | Planned |  | 3 | 2026-05-25 | 2026-05-28 | [5 empty] | ■
8.2.1 | Informal demo to PM team | Steven + Jenn | Planned |  | 1 | 2026-05-25 | 2026-05-25
8.2.2 | SVP Engineering presentation | Steven | Planned | VYRA Visualize demo | 1 | 2026-05-27 | 2026-05-27 | [5 empty] | ■
8.2.3 | Follow-up + next steps | Steven + Jenn | Planned |  | 1 | 2026-05-28 | 2026-05-28 | [5 empty] | ■

## Integration Map
Nova — Integration Map (25 Services)
Every external service, API, and dependency — with credentials, status, and notes
Category | Service | Used For | Credential / Config | Status | Notes
AI / LLM | OpenRouter | Kimi K2.5 (Stages 1,3), GLM-5 (Stage 4) | OPENROUTER_API_KEY | Active | Paid API — check quota monthly
AI / Image | NVIDIA NIM | Seedream 4.5 image gen (Stage 2) | NVIDIA_NIM_API_KEY (x15) | Active | Free tier keys, rotate monthly
AI / VQA | Gemma 4 | Visual quality assurance (Stages 2,4) | Via OpenRouter or NIM | Active | Pass threshold: 0.85
AI / Video | Kling 3.0 | UGC video generation (Stage 5) | KLING_ACCESS_KEY + SECRET | Credits needed | Paid API, scale requires credits
AI / Local | MLX (Apple Silicon) | Local LLM/VLM fallback | N/A (Metal GPU) | Active | Not available in Docker
AI / Local | Coqui TTS | Text-to-speech (Stage 5) | N/A (local) | Planned | XTTS-v2, 17 languages
AI / Local | Wav2Lip | Lip sync for video (Stage 5) | N/A (local torch) | Planned | Requires GPU
CMS | WordPress | Job CPT, ACF repeater, Yoast SEO | WP_USERNAME + WP_APP_PASSWORD | Active | REST API v2, ACF REST enabled
Auth | Clerk | User auth, SSO, roles | CLERK_SECRET_KEY + PUB_KEY | Active (dev) | Swap to prod after Azure AD
Auth | Azure AD (SAML) | Enterprise SSO for Centific | SAML metadata URL from IT | Not Started | Blocks internal rollout
Database | Neon Postgres | Primary data store + job queue | DATABASE_URL | Active | PASSWORD ROTATION NEEDED
Storage | Vercel Blob | Image, HTML, file storage | BLOB_READ_WRITE_TOKEN | Active | Public + private blobs
Hosting | Vercel | Next.js hosting, serverless functions | Vercel CLI auth | Active | nova-intake.vercel.app
Hosting | Azure VM | Worker container (China team) | Azure subscription | Planned | Docker multi-arch ready
Notifications | Microsoft Teams | Adaptive card notifications | TEAMS_WEBHOOK_URL | Active (test) | Need prod webhook from IT
Notifications | Outlook / Graph | Email from @centific.com | Graph API app registration | Not Started | Need IT to register app
Design | Figma | Push creatives for designer | Personal Access Token | Active | figma-api npm package
Rendering | Playwright | HTML→PNG composition | N/A (headless browser) | Active | Bundled in Docker image
Rendering | FFmpeg | Video/audio muxing | N/A (system binary) | Active | Bundled in Docker image
DNS | go.oneforma.com | Branded short link domain | CNAME → cname.vercel-dns.com | Pending IT | Cosmetic — works without it
Analytics | Google Analytics 4 | Campaign attribution | GA4 property + service acct | Planned (Phase 2) | VYRA Visualize dependency
Analytics | Meta Marketing API | FB/IG ad performance | Meta Business Manager | Planned (Phase 2) | VYRA Visualize dependency
Analytics | LinkedIn Marketing | LinkedIn ad performance | LinkedIn Campaign Manager | Planned (Phase 2) | VYRA Visualize dependency
Analytics | Google Ads API | Search/Display performance | Google Ads account | Planned (Phase 2) | VYRA Visualize dependency
File Storage | SharePoint Online | Auto-save approved assets | Graph API Sites.ReadWrite | Not Started | P2 — nice to have